ContextCast

Hyperlocal AI Event Intelligence Platform

Full Project Plan — Architecture · ML/MLOps · Requirements · Roadmap

| Project | ContextCast — Hyperlocal AI Event Intelligence Platform |
| --- | --- |
| Version | 1.0 |
| Author | Arnav |
| Status | Active Planning |
| Stack | FastAPI · React · PostgreSQL+pgvector · Kafka · Celery · MLflow · Redis |
| Compute | CPU-local (dev/lightweight models) + Online GPU (Colab / Modal / Replicate) |

# Table of Contents

1.  Project Overview & Vision	3

2.  Problem Statement	3

3.  Goals & Success Metrics	4

4.  Functional Requirements	4

5.  Non-Functional Requirements	6

6.  System Architecture — Overview	6

7.  Data Ingestion Pipeline	7

8.  NLP Enrichment Pipeline	8

9.  AI / ML — Recommendation Engine	9

10.  MLOps Infrastructure	11

11.  Backend Serving Layer	13

12.  Frontend Architecture	14

13.  Compute Strategy (CPU vs GPU)	14

14.  Database Design	15

15.  API Specification	16

16.  Security & Auth	17

17.  Sprint Plan & Build Roadmap	17

18.  Folder Structure	19

19.  CV Bullet Points	20

20.  Risk Register	20

# 1.  Project Overview & Vision

ContextCast is a full-stack, AI-first web platform that solves hyper-local event discovery. Existing solutions — Eventbrite, Facebook Events, Meetup — surface popular events based on keyword search or broad category filters. They miss the long tail: niche tech talks, informal hackathons posted on Reddit, college fests buried on notice boards, open-mic nights mentioned in a WhatsApp channel.

ContextCast aggregates these unstructured, heterogeneous sources, runs a multi-stage AI pipeline to extract, classify, embed, and rank events, then delivers a personalised feed to each user with an explainable match score. The platform is architected as a real, production-grade system — not a tutorial CRUD app — with a data engineering backbone, an ML recommendation engine, and a full MLOps lifecycle.

| Vision | Any user in any city sees the five events most relevant to them today — sourced from the entire noisy internet, explained in plain English, ranked by a model that learns their taste. |
| --- | --- |

# 2.  Problem Statement

The core problem has three dimensions:

- Fragmentation — Events are announced across Reddit threads, RSS feeds, college websites, Telegram groups, Twitter, and Eventbrite. No single surface aggregates them.

- Signal-noise ratio — Scraped text is unstructured and noisy. A Reddit post might mention an event in the third paragraph. A college notice board uses inconsistent date formats.

- Generic ranking — Even when events are found, ranking by popularity or recency ignores personal interest. A Python developer doesn't want a generic 'Tech Events' list — they want the rustlang workshop on Saturday.

| Core Insight | The problem is not data scarcity — it's data chaos + one-size-fits-all ranking. ContextCast solves both. |
| --- | --- |

# 3.  Goals & Success Metrics

## 3.1  Product Goals

- Ingest 4+ unstructured event sources daily with zero manual curation

- Produce a personalised top-10 feed per user, refreshed every 10 minutes

- Provide a 1-line natural language explanation per recommended event

- Build a user interest graph that improves recommendations on every interaction

- Show a real-time pipeline health dashboard and model performance monitor

## 3.2  Engineering Goals

- Full async ingestion + enrichment pipeline with Kafka decoupling

- Sub-200ms p95 API response time for feed endpoint

- Model versioning, experiment tracking, and automated retraining hooks

- Reproducible ML experiments via MLflow, deployable to CPU or GPU

## 3.3  Success Metrics

| Metric | Target | How Measured |
| --- | --- | --- |
| Feed latency (p95) | < 200ms | FastAPI middleware timing |
| Enrichment accuracy (NER) | > 85% F1 on held-out set | Offline eval vs hand-labelled 200 events |
| Topic classification accuracy | > 80% on 10 classes | Zero-shot vs fine-tuned baseline |
| ANN retrieval recall@10 | > 0.90 | Offline eval vs brute-force cosine |
| Click-through rate (CTR) | > 15% on top-3 recommendations | Interaction log analysis |
| Pipeline uptime | > 99% | Health-check endpoint + alerting |
| Retraining latency | < 30 min end-to-end | MLflow run timestamps |

# 4.  Functional Requirements

## 4.1  Data Ingestion

- FR-I-01: System MUST crawl r/chennai, r/bangalore, r/delhi (configurable) for event-related posts every 6 hours via PRAW

- FR-I-02: System MUST ingest Meetup.com and Eventbrite RSS feeds every 2 hours via feedparser

- FR-I-03: System MUST scrape 3+ configurable college notice board URLs via Playwright (headless Chrome) every 12 hours

- FR-I-04: All raw items MUST be deduplicated using a SHA-256 fingerprint of (source + title + date_hint) before enqueue

- FR-I-05: Raw items MUST be published to a Kafka topic 'raw-events' with source metadata

## 4.2  NLP Enrichment

- FR-E-01: System MUST extract event date, venue, title, and topic tags from raw text using spaCy NER

- FR-E-02: System MUST classify each event into 10 topic categories (tech, music, art, sports, community, food, film, comedy, education, other) using zero-shot classification

- FR-E-03: System MUST generate a 384-dimensional dense embedding per event using sentence-transformers

- FR-E-04: Events failing confidence threshold (< 0.45 on topic classification) MUST be marked 'low-confidence' and excluded from main feed

- FR-E-05: Enriched events MUST be stored in PostgreSQL with pgvector extension (events.embedding column)

## 4.3  Recommendation Engine

- FR-R-01: System MUST maintain a per-user interest vector (384-dim, exponential moving average of attended/clicked event embeddings)

- FR-R-02: ANN retrieval MUST return top-100 candidates using pgvector HNSW index (ef_search=64)

- FR-R-03: Re-ranker MUST apply: (a) cosine similarity score, (b) proximity decay by haversine distance, (c) recency decay (exponential half-life 7 days), (d) interest graph affinity weight

- FR-R-04: Final top-10 events per user MUST each carry an explainability payload generated by LLM (Claude API or GPT-4o)

- FR-R-05: Cold-start users (< 3 interactions) MUST receive onboarding interest picker; their initial vector MUST be seeded from selected interest centroids

## 4.4  User & Auth

- FR-U-01: Users MUST register/login via email+password or Google OAuth

- FR-U-02: JWT access token (15 min TTL) + refresh token (7-day TTL, httpOnly cookie)

- FR-U-03: Users MAY set a home city and radius (km) for proximity scoring

- FR-U-04: Users MAY rate events (save / not interested) — these signals MUST update their interest vector

## 4.5  Frontend

- FR-F-01: Feed page MUST render top-10 event cards with match score, topic chip, venue, date, and 'Why this?' explainability tooltip

- FR-F-02: Interest map page MUST render a D3 force-directed graph of user ↔ topic ↔ event nodes

- FR-F-03: Admin dashboard MUST show pipeline run status, enrichment stats, model drift indicator, and last retrain timestamp

- FR-F-04: Real-time notifications MUST push new highly-matching events via WebSocket

# 5.  Non-Functional Requirements

| Category | Requirement | Target |
| --- | --- | --- |
| Performance | Feed API p95 latency | < 200ms |
| Performance | Enrichment throughput | > 100 events/min per worker |
| Scalability | Celery workers | Horizontally scalable (add replicas) |
| Reliability | Kafka retention | 7 days (replay on worker crash) |
| Reliability | DB connection pool | min 5, max 20 connections |
| Security | JWT signing | RS256 asymmetric key |
| Security | Rate limiting | 60 req/min per user (Redis sliding window) |
| Observability | Structured logs | JSON via structlog, shipped to Loki |
| Observability | Metrics | Prometheus + Grafana dashboards |
| Observability | Tracing | OpenTelemetry spans on every pipeline stage |
| ML | Model versioning | All experiments tracked in MLflow |
| ML | Drift detection | Jensen-Shannon divergence on embedding distributions |
| Portability | Containerised | Docker Compose for all services |

# 6.  System Architecture — Overview

ContextCast is composed of five logical layers. Each layer is independently deployable and communicates via well-defined interfaces (Kafka topics, REST APIs, PostgreSQL schemas).

LAYER 1 — DATA INGESTION

| Reddit / PRAW | → | RSS / feedparser | → | Playwright | → | Kafka Topic |
| --- | --- | --- | --- | --- | --- | --- |
| r/city subreddits |  | Meetup + Eventbrite |  | College notice boards |  | raw-events |

LAYER 2 — NLP ENRICHMENT WORKERS (Celery)

| Consume | → NER | → Classify | → Embed | → Store |
| --- | --- | --- | --- | --- |
| raw-events topic | spaCy trf model | BART-MNLI zero-shot | sentence-transformers | PostgreSQL + pgvector |

LAYER 3 — RECOMMENDATION & ML (Intelligence Core)

| User Vector | → ANN | → Re-rank | → Explain | → Cache |
| --- | --- | --- | --- | --- |
| Interest EMA | pgvector HNSW | 4-signal scorer | LLM 1-liner | Redis TTL 10m |

LAYER 4 — MLOPS (Lifecycle Management)

| MLflow | DVC | Evidently | Modal / Colab | Prometheus |
| --- | --- | --- | --- | --- |
| Experiment tracking | Data versioning | Drift detection | GPU retraining | Model metrics |

LAYER 5 — SERVING & FRONTEND

| FastAPI | → Redis | → React | → D3.js | → Grafana |
| --- | --- | --- | --- | --- |
| REST + WebSocket | Cache + sessions | Vite + Tailwind | Interest graph viz | Ops dashboard |

# 7.  Data Ingestion Pipeline

## 7.1  Sources & Crawlers

| Source | Method | Schedule | Library | Estimated Volume |
| --- | --- | --- | --- | --- |
| Reddit city subreddits | PRAW streaming + periodic fetch | Every 6h | praw 7.x | 50–200 posts/run |
| Meetup.com | RSS feed parse | Every 2h | feedparser | 10–80 events/run |
| Eventbrite | RSS + scrape | Every 4h | feedparser + httpx | 20–100 events/run |
| College notice boards | Headless browser scrape | Every 12h | Playwright (chromium) | 5–40 posts/run |
| Future: Twitter/X API | v2 filtered stream | Real-time | tweepy | TBD |

## 7.2  Deduplication

Every raw item is fingerprinted before publishing. The fingerprint is SHA-256 of (source_id + title_normalised + date_hint_normalised). Redis SET is checked before Kafka publish — if the key exists (TTL 7 days), the item is dropped. This prevents the same event from being enriched multiple times across crawl windows.

## 7.3  Kafka Topic Design

| Topic | Partitions | Retention | Consumers | Key |
| --- | --- | --- | --- | --- |
| raw-events | 4 | 7 days | enrichment-worker group | source_id |
| enriched-events | 4 | 3 days | recommendation-worker group | event_id |
| user-interactions | 2 | 30 days | interest-graph-updater | user_id |

# Raw event schema (Kafka message value — JSON) { 'source': 'reddit', 'source_id': 't3_abc123', 'raw_text': '...full post body...', 'url': 'https://reddit.com/r/bangalore/...', 'fetched_at': '2025-06-10T14:32:00Z', 'fingerprint':'sha256:...' }

# 8.  NLP Enrichment Pipeline

## 8.1  Architecture

Enrichment workers are Celery consumers subscribed to the 'raw-events' Kafka topic. Each worker runs on CPU and processes one event at a time through a sequential NLP chain. All models are loaded once at worker startup and kept in memory.

## 8.2  Stage 1 — Named Entity Recognition (spaCy)

- Model: en_core_web_trf (transformer-based, runs on CPU, ~85MB)

- Extracts: DATE, TIME, GPE (location), ORG entities from raw text

- Custom pipeline component added for event-specific patterns (e.g., 'Register by', 'Venue:')

- Output: structured dict {title, date_str, venue_hint, organiser}

## 8.3  Stage 2 — Zero-Shot Topic Classification (facebook/bart-large-mnli)

This is the most technically interesting enrichment step. Instead of training a custom classifier (which would require labelled data), we use zero-shot classification via entailment: the model is asked whether the event text 'entails' each candidate label.

from transformers import pipeline classifier = pipeline('zero-shot-classification', model='facebook/bart-large-mnli', device=-1) # CPU labels = ['technology', 'music', 'art', 'sports', 'community', 'food', 'film', 'comedy', 'education', 'other'] result = classifier(event_text, candidate_labels=labels) # Returns: {'labels': [...sorted by score...], 'scores': [...]} # Top label used if score > 0.45, else 'low-confidence'

| CPU Note | bart-large-mnli runs in ~1.2s per event on CPU. With 4 Celery workers, pipeline throughput is ~200 events/min — sufficient for all source volumes. |
| --- | --- |

## 8.4  Stage 3 — Dense Embedding (sentence-transformers)

- Model: all-MiniLM-L6-v2  (22MB, CPU-optimised, 384-dim output)

- Input: concatenation of event title + first 200 chars of description

- Output: 384-dim float32 vector, L2-normalised, stored in pgvector column

- Batch size: 32 events per encode call for throughput

## 8.5  Quality Filter

- Events with classification confidence < 0.45 are flagged 'low_confidence'

- Events with no extractable date (NER finds no DATE entity) are flagged 'no_date'

- Flagged events stored but excluded from recommendation feed; shown in admin panel for review

# 9.  AI / ML — Recommendation Engine

## 9.1  User Interest Vector

Each user is represented as a 384-dimensional interest vector — the same dimensionality as the event embeddings. This vector is initialised from the centroid of events in the user's selected interest categories (cold-start). It is updated using an Exponential Moving Average (EMA) on every positive interaction (click, save, attend):

# EMA update on each positive interaction ALPHA = 0.15 # learning rate — higher = adapts faster def update_user_vector(current_vec, event_embedding, alpha=ALPHA): new_vec = (1 - alpha) * current_vec + alpha * event_embedding return normalise(new_vec) # keep unit length for cosine similarity # Negative interaction (Not Interested) = repulsion def repel_user_vector(current_vec, event_embedding, alpha=0.05): new_vec = current_vec - alpha * event_embedding return normalise(new_vec)

## 9.2  ANN Retrieval — pgvector HNSW Index

Rather than computing cosine similarity against all events (slow at scale), we use Hierarchical Navigable Small World (HNSW) — an approximate nearest neighbour index built into pgvector. This trades a small recall penalty (< 5%) for a 100x speedup.

-- Create HNSW index on event embeddings CREATE INDEX events_embedding_hnsw ON events USING hnsw (embedding vector_cosine_ops) WITH (m=16, ef_construction=64); -- ANN query: top 100 candidates for a user vector SET hnsw.ef_search = 64; SELECT id, title, 1 - (embedding <=> $1::vector) AS similarity FROM events WHERE status = 'active' ORDER BY embedding <=> $1::vector LIMIT 100;

## 9.3  Four-Signal Re-Ranker

The 100 ANN candidates are re-scored by a weighted composite function. This is where domain knowledge and ML principles combine:

| Signal | Formula | Weight | Rationale |
| --- | --- | --- | --- |
| Semantic similarity | cosine(user_vec, event_vec) | 0.40 | Core relevance — how semantically close is this event to the user's taste |
| Proximity decay | exp(-distance_km / radius_km) | 0.25 | Nearby events rank higher; decays exponentially beyond user's preferred radius |
| Recency decay | exp(-days_until_event / 7) | 0.20 | Events further in future rank lower; half-life = 7 days |
| Graph affinity | graph_edge_weight(user, topic) | 0.15 | How strongly connected is the user to this event's topic in the interest graph |

def rerank(candidates, user, weights=(0.40, 0.25, 0.20, 0.15)): scored = [] for e in candidates: s1 = e.cosine_score s2 = proximity_score(user.lat, user.lon, e.lat, e.lon, user.radius_km) s3 = recency_score(e.event_date) # exponential decay s4 = graph_affinity(user.id, e.topic, G) # NetworkX query final = sum(w*s for w,s in zip(weights,[s1,s2,s3,s4])) scored.append((e, final)) return sorted(scored, key=lambda x: -x[1])[:10]

## 9.4  Interest Graph (NetworkX)

A directed weighted graph is maintained per user. Nodes are users and topics; edges carry a weight representing the strength of association (incremented on each positive interaction, decayed over time). This graph is serialised to PostgreSQL as a JSON blob and loaded into memory per recommendation request.

- Node types: User (1 per user), Topic (10 fixed), EventCluster (k-means cluster id of event embeddings)

- Edge update: weight += 1.0 on click; weight += 2.0 on save; weight *= 0.98 daily (temporal decay)

- Graph affinity score = normalised outgoing edge weight from user → topic node

## 9.5  LLM Explainability Layer

For each of the top-10 recommendations, a one-line natural language explanation is generated by calling the Claude API (or GPT-4o). The prompt is structured to produce a user-facing reason, not a technical description:

SYSTEM: You are an event recommendation assistant. Given a user's interest profile and an event, write ONE sentence (max 15 words) explaining why this event matches them. Be specific, not generic. USER: User interests: Python, backend engineering, open-source Clicked events: 'Rust Systems Workshop', 'PyCon India 2024' Event: 'FastAPI Deep Dive — Building Production APIs' Topic: Technology Similarity score: 0.87 ASSISTANT: Because you attended PyCon India and love backend engineering, this FastAPI workshop is a natural next step.

# 10.  MLOps Infrastructure

MLOps is what separates this project from a basic ML demo. ContextCast implements a full ML lifecycle: experiment tracking, data versioning, model registry, drift detection, and automated retraining — split across CPU (local dev) and GPU (cloud).

## 10.1  Experiment Tracking — MLflow

- Every training run (embedding model fine-tuning, re-ranker weight search, classifier eval) is logged to an MLflow Tracking Server

- Tracked: hyperparameters (alpha, HNSW ef_search, re-rank weights), metrics (Recall@K, MRR, NDCG@10), and artefacts (model weights, confusion matrix PNG)

- MLflow UI served at localhost:5000 in dev; hosted on Render in staging

import mlflow with mlflow.start_run(run_name='reranker_weight_sweep_v3'): mlflow.log_params({'alpha': 0.15, 'weights': [0.40,0.25,0.20,0.15]}) recall_at_10 = evaluate_reranker(test_interactions) mlflow.log_metric('recall@10', recall_at_10) mlflow.log_metric('ndcg@10', ndcg_score(test_interactions)) mlflow.sklearn.log_model(reranker, 'reranker_model') # Register best model mlflow.register_model('runs:/{}/reranker_model'.format(run_id), 'ContextCast-Reranker')

## 10.2  Data Versioning — DVC

- Raw crawled event dumps (Parquet) are tracked with DVC, remote stored on Google Drive or S3

- Enables reproducible experiments: checkout data version → retrain → compare metrics

- dvc.yaml pipeline defines stages: ingest → enrich → embed → train → eval

# dvc.yaml — reproducible ML pipeline stages: embed: cmd: python scripts/embed_events.py --input data/enriched.parquet deps: [scripts/embed_events.py, data/enriched.parquet] outs: [data/embeddings.npy] eval_reranker: cmd: python scripts/eval_reranker.py deps: [data/embeddings.npy, data/interactions.parquet] metrics: [metrics/reranker_eval.json]

## 10.3  Drift Detection — Evidently AI

Model drift is monitored in two dimensions: data drift (distribution of incoming event embeddings shifting over time) and prediction drift (distribution of recommendation scores changing). Evidently AI generates HTML reports and JSON metrics on a daily schedule.

- Embedding distribution drift: Jensen-Shannon divergence between rolling 7-day window and reference window

- Score drift: KS test on distribution of re-ranker final scores

- Threshold: JS divergence > 0.15 or KS p-value < 0.05 triggers retraining alert

- Reports stored as artefacts in MLflow and rendered in admin dashboard

## 10.4  Retraining Pipeline — CPU vs GPU Split

Retraining is split based on compute requirements:

| Task | Compute | Platform | When |
| --- | --- | --- | --- |
| Re-ranker weight optimisation (scipy) | CPU | Local / Render worker | Weekly or on drift alert |
| User vector batch recompute | CPU | Celery beat task | Daily 2AM |
| Interest graph rebuild | CPU | Celery beat task | Every 6h |
| Embedding model fine-tuning (sentence-transformers) | GPU (T4) | Google Colab / Modal | Monthly or on metric drop |
| Zero-shot classifier fine-tune (if adding custom labels) | GPU (T4/A10) | Modal.com | On-demand |
| Offline evaluation suite | CPU | GitHub Actions CI | On every PR to main |

## 10.5  Modal.com Integration (GPU on-demand)

import modal stub = modal.Stub('contextcast-finetune') image = modal.Image.debian_slim().pip_install( 'sentence-transformers', 'datasets', 'mlflow') @stub.function(gpu='T4', image=image, timeout=3600) def finetune_embedder(train_data_path: str, run_name: str): from sentence_transformers import SentenceTransformer, losses model = SentenceTransformer('all-MiniLM-L6-v2') # ... training loop ... mlflow.log_metric('val_cosine_similarity', val_score) model.save('/tmp/finetuned_embedder') # Upload to model registry

## 10.6  Observability Stack

- Prometheus — scrapes FastAPI /metrics endpoint (custom: feed_latency_histogram, enrichment_throughput, drift_score)

- Grafana — 3 dashboards: (1) API health, (2) pipeline throughput, (3) ML model metrics

- Loki — structured JSON logs from all services, queried in Grafana

- OpenTelemetry — distributed traces from API → recommendation engine → DB query

- Alertmanager — PagerDuty/Slack alert on drift threshold breach or pipeline failure

# 11.  Backend Serving Layer

## 11.1  FastAPI Application Structure

app/ ├── api/ │ ├── v1/ │ │ ├── feed.py # GET /feed — personalised event feed │ │ ├── events.py # GET /events/{id}, POST /events/interact │ │ ├── users.py # GET/PUT /users/me │ │ ├── auth.py # POST /auth/login, /auth/refresh │ │ └── admin.py # GET /admin/pipeline, /admin/drift ├── core/ │ ├── recommendation.py # orchestrates ANN + rerank + explain │ ├── interest_graph.py # NetworkX graph CRUD │ └── explainer.py # LLM API call + caching ├── workers/ │ ├── enrichment.py # Celery consumer: NER + classify + embed │ ├── graph_updater.py # Celery task: update interest graph on click │ └── scheduler.py # APScheduler: crawl cron jobs ├── db/ │ ├── models.py # SQLAlchemy ORM models │ └── session.py # async connection pool └── main.py # FastAPI app init, lifespan, middleware

## 11.2  Caching Strategy

- Feed cache: user's top-10 feed cached in Redis with key 'feed:{user_id}', TTL 10 minutes

- Explanation cache: LLM explanations cached with key 'explain:{event_id}:{user_topic_hash}', TTL 24h (explanations are semi-deterministic)

- User vector cache: current interest vector cached with TTL 5 min — invalidated on any interaction

- Pipeline stats cache: admin dashboard data cached 60 seconds

# 12.  Frontend Architecture

## 12.1  Pages & Components

| Page / Component | Description | Key Tech |
| --- | --- | --- |
| / Onboarding | Interest picker for cold-start users (topic chips, city selector) | React, Framer Motion |
| /feed | Main event feed — card list with match score, topic chip, explainability tooltip | React Query, Tailwind |
| /events/:id | Event detail — full description, venue map, 'Why this?' breakdown | Mapbox GL, React |
| /graph | Interactive interest map — D3 force-directed graph of user↔topic↔event | D3.js, canvas render |
| /profile | User settings — city, radius, preferences, interaction history | React Hook Form |
| /admin | Pipeline dashboard — Grafana embed + custom React stats cards | Recharts, Grafana iframe |

## 12.2  State Management

- React Query (TanStack Query) for all server state — automatic cache invalidation, background refetch

- Zustand for local UI state (selected filters, map viewport, onboarding step)

- WebSocket connection managed in a singleton hook — pushes new events to feed without full refetch

# 13.  Compute Strategy — CPU vs Online GPU

| Principle | Run everything that's feasible on CPU (lower latency, no cold start, free). Delegate only genuine GPU-necessary tasks to cloud GPU. Keep costs near zero. |
| --- | --- |

| Task | Model Size | CPU Time | GPU Time | Runs On | Why |
| --- | --- | --- | --- | --- | --- |
| Dense embedding (inference) | 22MB | ~30ms/event | ~3ms/event | CPU (always) | Fast enough; no cold start |
| Zero-shot classify (inference) | 890MB | ~1.2s/event | ~0.1s/event | CPU (workers) | 1.2s acceptable at batch scale |
| spaCy NER | ~80MB | ~50ms/event | N/A | CPU (always) | Too small to need GPU |
| Interest graph update | In-memory | <5ms | N/A | CPU (always) | Pure math |
| Re-ranker scoring | Scipy/numpy | <10ms | N/A | CPU (always) | No neural net |
| Embedding fine-tuning | 22MB→train | ~4h/epoch | ~8min/epoch | Colab/Modal GPU | Only monthly |
| Classifier fine-tune (if needed) | 890MB→train | Infeasible | ~30min | Modal A10 | Only on-demand |
| Offline eval suite | All models | ~20min | N/A | GitHub Actions (CPU) | Runs on PR |

## 13.1  Google Colab Workflow

- Notebook: contextcast/notebooks/finetune_embedder.ipynb committed to repo

- Reads training data from DVC remote (Google Drive) — no data upload needed

- Trains, logs to MLflow (MLFLOW_TRACKING_URI env var pointed at cloud MLflow)

- Saves model to Google Drive; CI downloads artefact and runs eval

## 13.2  Modal.com Workflow (Preferred for automation)

- modal run scripts/finetune_modal.py — spins up T4 GPU, runs training, tears down automatically

- Triggered manually or via GitHub Actions on drift alert

- Cost: ~$0.60/hour for T4; monthly fine-tune run costs < $2

# 14.  Database Design

## 14.1  Core Tables

-- Events (core table) CREATE TABLE events ( id UUID PRIMARY KEY DEFAULT gen_random_uuid(), source TEXT NOT NULL, -- 'reddit'¦'meetup'¦'eventbrite'¦'scrape' source_id TEXT NOT NULL, title TEXT NOT NULL, description TEXT, event_date TIMESTAMPTZ, venue_name TEXT, lat FLOAT, lon FLOAT, topic TEXT NOT NULL, -- classified label confidence FLOAT, -- classifier confidence status TEXT DEFAULT 'active', -- 'active'¦'low_confidence'¦'expired' embedding VECTOR(384), -- pgvector column fetched_at TIMESTAMPTZ DEFAULT NOW(), UNIQUE(source, source_id) ); -- User interest vectors + graph CREATE TABLE user_profiles ( user_id UUID PRIMARY KEY REFERENCES users(id), interest_vec VECTOR(384), interest_graph JSONB, -- serialised NetworkX graph home_lat FLOAT, home_lon FLOAT, radius_km INT DEFAULT 30, updated_at TIMESTAMPTZ DEFAULT NOW() ); -- Interactions (click, save, not_interested) CREATE TABLE interactions ( id UUID PRIMARY KEY DEFAULT gen_random_uuid(), user_id UUID REFERENCES users(id), event_id UUID REFERENCES events(id), action TEXT, -- 'click'¦'save'¦'attend'¦'not_interested' created_at TIMESTAMPTZ DEFAULT NOW() );

# 15.  API Specification — Key Endpoints

| Method | Endpoint | Auth | Description | Response |
| --- | --- | --- | --- | --- |
| POST | /auth/login | None | Email+pass login, returns JWT | { access_token, refresh_token } |
| GET | /feed | JWT | Returns personalised top-10 events with scores + explanations | { events[], generated_at } |
| POST | /events/{id}/interact | JWT | Log click/save/not_interested — triggers async vector update | { success: true } |
| GET | /events/{id} | JWT | Full event detail | Event object |
| GET | /users/me/graph | JWT | Returns interest graph nodes+edges for D3 viz | { nodes[], edges[] } |
| GET | /admin/pipeline | JWT+Admin | Pipeline run stats, enrichment counts, drift score | Admin stats object |
| WS | /ws/feed | JWT | WebSocket — pushes new high-match events in real-time | Event objects |

# 16.  Security & Authentication

- JWT signed with RS256 (asymmetric) — public key served at /.well-known/jwks.json

- Access token TTL: 15 minutes. Refresh token: 7 days, stored in httpOnly Secure cookie

- Rate limiting: 60 req/min per user via Redis sliding window counter

- Input sanitisation: all text inputs passed through bleach before storage

- Crawlers run with a configurable robots.txt check; User-Agent identifies bot

- LLM API key stored in environment variable, never committed to repo

- Secrets management: python-dotenv in dev; Railway/Render secret groups in staging

# 17.  Sprint Plan & Build Roadmap

12 sprints × 1 week each. Work estimate assumes ~15–20 hours/week solo developer.

| Sprint | Theme | Deliverables | Tech / Tools |
| --- | --- | --- | --- |
| S01 | Foundations | Docker Compose, PostgreSQL+pgvector, Redis, Kafka, FastAPI skeleton, Auth (JWT), basic user table | FastAPI, Docker, PostgreSQL, pgvector, python-jose |
| S02 | Reddit + RSS Crawlers | PRAW crawler, feedparser RSS ingestor, dedup fingerprint, Kafka producer, raw_events table | PRAW, feedparser, kafka-python, SHA-256 |
| S03 | Playwright Scraper | Playwright college notice board scraper, APScheduler cron jobs, admin trigger endpoint, crawl health logging | Playwright, APScheduler, structlog |
| S04 | NLP Enrichment Worker | spaCy NER pipeline, zero-shot classifier (bart-mnli), Celery consumer, enriched_events table, quality filter | spaCy, transformers, Celery, Redis |
| S05 | Embeddings + pgvector | sentence-transformers encode, pgvector HNSW index, ANN retrieval query, offline recall eval script | sentence-transformers, pgvector, numpy |
| S06 | Interest Graph + User Vector | User vector EMA update, NetworkX graph CRUD, cold-start seeding, interaction endpoint, async vector update task | NetworkX, numpy, Celery |
| S07 | Re-Ranker + Feed API | 4-signal re-ranker, final scoring + sort, /feed endpoint, Redis feed cache (TTL 10m), feed response schema | FastAPI, Redis, scipy |
| S08 | LLM Explainability | Claude/GPT-4o API integration, explanation prompt, response caching, 'Why this?' payload in feed response | anthropic / openai SDK, Redis |
| S09 | MLflow + DVC Setup | MLflow tracking server, DVC pipeline (dvc.yaml), log re-ranker eval run, register model, Evidently drift report | MLflow, DVC, Evidently AI |
| S10 | Modal GPU Fine-tune + CI Eval | sentence-transformers fine-tune on Colab/Modal, dvc repro, GitHub Actions eval on PR, MLflow model comparison | Modal, GitHub Actions, MLflow |
| S11 | React Frontend | Feed page (event cards + match score), onboarding interest picker, D3 interest graph, WebSocket integration, admin dashboard | React, Vite, Tailwind, D3.js, TanStack Query |
| S12 | Observability + Polish | Prometheus metrics, Grafana dashboards (3), Loki logging, drift alert webhook, load test (locust), README + demo | Prometheus, Grafana, Loki, locust |

# 18.  Repository Folder Structure

contextcast/ ├── backend/ │ ├── app/ │ │ ├── api/v1/ # FastAPI routers │ │ ├── core/ # recommendation, graph, explainer │ │ ├── workers/ # Celery tasks + scheduler │ │ ├── db/ # SQLAlchemy models + session │ │ └── main.py │ ├── scripts/ │ │ ├── crawlers/ # reddit.py, rss.py, playwright_scraper.py │ │ ├── embed_events.py │ │ ├── eval_reranker.py │ │ └── finetune_modal.py │ └── Dockerfile ├── frontend/ │ ├── src/ │ │ ├── pages/ # Feed, Graph, Profile, Admin, Onboarding │ │ ├── components/ # EventCard, InterestMap, WhyThisTooltip │ │ ├── hooks/ # useFeed, useWebSocket, useGraph │ │ └── stores/ # zustand stores │ └── Dockerfile ├── notebooks/ │ └── finetune_embedder.ipynb # Colab/GPU fine-tuning notebook ├── data/ # DVC-tracked (not committed) │ ├── raw/ # Parquet: raw crawled events │ ├── enriched/ # Parquet: enriched events │ └── interactions/ # Parquet: user interactions ├── metrics/ # DVC metrics: reranker_eval.json etc. ├── mlflow/ # MLflow local tracking store ├── infra/ │ ├── docker-compose.yml # Full stack local dev │ ├── prometheus.yml │ └── grafana/dashboards/ ├── .github/workflows/ │ ├── eval.yml # Eval on PR │ └── deploy.yml # Deploy on main merge ├── dvc.yaml # DVC pipeline definition ├── dvc.lock └── README.md

# 19.  CV Bullet Points

| Note | These are the exact bullet points to put on your resume under 'Projects'. Each one is precise, metric-backed, and uses the right keywords. |
| --- | --- |

- Architected a real-time hyperlocal event intelligence platform ingesting 4 unstructured sources (Reddit, RSS, Playwright scrapes) via Kafka, enriching 500+ events/day through a 3-stage NLP pipeline: spaCy NER → zero-shot BART-MNLI classification → sentence-transformer embedding

- Designed a three-stage hybrid recommender: pgvector HNSW ANN retrieval (top-100 candidates) → 4-signal re-ranker (semantic similarity, proximity decay, recency decay, graph affinity) → LLM explainability layer via Claude API; feed p95 latency < 200ms

- Modelled user taste as a 384-dim interest vector updated via EMA on every interaction, and a NetworkX weighted graph of user↔topic associations — solving cold-start via centroid seeding

- Implemented a complete MLOps lifecycle: MLflow experiment tracking, DVC data versioning, Evidently AI drift detection (JS divergence threshold), and automated GPU fine-tuning of sentence-transformers on Modal.com (T4, ~$2/month)

- Built full observability stack: Prometheus metrics, Grafana dashboards (API health, pipeline throughput, ML drift), Loki structured logging, OpenTelemetry distributed tracing across 6 services

- Containerised all services (Docker Compose: 9 containers) with horizontal Celery worker scaling; CI runs offline eval suite (Recall@10, NDCG@10, MRR) on every PR via GitHub Actions

# 20.  Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Reddit API rate limits break crawler | Medium | High | Implement exponential backoff; cache PRAW session; use pushshift.io as fallback |
| bart-mnli too slow on CPU for volume spikes | Medium | Medium | Batch classify in groups of 32; add worker replicas; cache classification results per fingerprint |
| pgvector HNSW recall degrades at scale | Low | High | Monitor recall@10 in offline eval; tune ef_search; rebuild index monthly |
| LLM API costs spike (explainability) | Medium | Medium | Cache explanations 24h per event; batch generate off-peak; set monthly spend cap |
| Playwright scraper breaks on website redesign | High | Low | Abstract selectors to config file; admin alert on zero-result scrape; easy to fix |
| Interest vector overfits to recent interactions | Medium | Medium | EMA alpha = 0.15 ensures slow drift; add 'explore' mode that temporarily widens retrieval |
| Model drift undetected | Low | High | Evidently AI daily report + Slack alert on JS divergence > 0.15; weekly manual review |

| You're building this | This document is your north star. Sprint 1 starts with Docker Compose + auth. Every sprint adds one layer. By Sprint 12 you have a portfolio centrepiece that no interviewer will skip past. |
| --- | --- |